## CP1 Gantt
Nomobug Capstone Project 1 Proposed Gantt Chart
Bars show planned work weeks. Edit start week and duration if timeline changes.
No. | Task Name | Description | Start Week | Duration | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15
1 | Project Initialization | Confirm project direction, scope and supervisor feedback | 1 | 2
2 | Background Study | Review Nomobug problem context and existing pest-control tools | 2 | 3
3 | Literature Review | Collect and review papers on spatio-temporal pest analytics, data engineering and BI | 3 | 5
4 | Data Understanding | Inspect Google Sheets, calendar exports, source columns and messy data issues | 5 | 3
5 | Methodology Design | Design analytics methods, data model, ETL workflow, architecture and evaluation plan | 7 | 4
6 | Proposal Writing | Write and refine Chapter 1 to Chapter 4 with citations and supervisor updates | 9 | 4
7 | Gantt and Architecture Visuals | Prepare CP1/CP2 Gantt workbook and technical stack flow diagram | 12 | 2
8 | Final Review and Submission | Proofread, format, standardise fonts and prepare submission files | 14 | 2

## CP2 Gantt
Nomobug Capstone Project 2 Proposed Gantt Chart
Bars show planned work weeks. Edit start week and duration if timeline changes.
No. | Task Name | Description | Start Week | Duration | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20
1 | Project Setup | Set up GitHub repo, Python environment, Airflow/dbt/Superset local stack and BigQuery project | 1 | 2
2 | Source Profiling | Profile Google Sheets, CSV exports, calendar events and weather API fields | 2 | 3
3 | Python Extraction and Staging | Build extraction scripts and load raw data into BigQuery bronze tables | 4 | 3
4 | Data Quality and Contracts | Implement source schema checks, validation flags and data quality report tables | 5 | 3
5 | dbt Transformations | Create silver facts/dimensions and tested SQL transformation models | 7 | 4
6 | Weather Enrichment | Match services to historical weather features and optional flood/current warning data | 8 | 3
7 | Analytics Marts | Build treatment difficulty, recurrence, hotspot, warranty review and upsell marts | 10 | 4
8 | Superset Dashboards | Create executive, quality, weather, recurrence, upsell and data quality dashboards | 12 | 4
9 | Recommendation Log | Create recommendation output table and management action/outcome tracking workflow | 14 | 2
10 | Testing and UAT | Run pipeline checks, dashboard verification, sample validation and company feedback session | 15 | 3
11 | Final Report and Presentation | Prepare CP2 report, presentation demo, limitations and future work | 17 | 3

## Summary
Nomobug Capstone Gantt Workbook
Purpose | Editable CP1 and CP2 timeline workbook for the proposal report. The chart can be screenshotted or copied into Word.
CP1 Focus | Proposal, literature review, methodology, data understanding, architecture, and planning.
CP2 Focus | Implementation, ETL, BigQuery, dbt, Superset dashboards, testing, and presentation.
Note | This is a proposed planning chart. Exact CP2 dates can be adjusted after supervisor approval.